## Sheet1
Date | #Hours | Task | Estimate | Sum | Running Total Left | Description | TAG
2009-08-09 | 4 | Graphics prep & PM | 10 | 6 | 157 | reorganizing photoshop file, speaking to Andre, planning approach
2009-08-12 | 3 | Graphics Prep & Email | 10 | 3 | 154 | Direct integration from photoshop to flash, attempted to convert vector paths from PS to AI... Didn't really work. Graphics should technically be vectors, but not enough time for me to change them. Emailed Andre about state of graphics
2009-08-13 | 1.5 | Graphics Prep | 10 | 1.5 | 152.5 | Integration of assets essentially complete. Expecting more assets and more changes.
2009-08-15 | 3 | Framework | 12 | 9 | 149.5 | Preparing the framework manager
2009-08-15 | 2 | Backend | 20 | 18 | 147.5 | backend data collection ( this is a stub object right now but will be converted to actual environment once this is known )
2009-08-16 | 5 | Framework | 12 | 4 | 142.5 | s
2009-08-16 | 6 | Backend | 20 | 12 | 136.5 | backend data collection ( will need to save remaining hours for database creation when I get it )
August 17,2009 | 2 | Framework | 12 | 2 | 134.5 | Framework research: Needed to do 2 hours of reading to ensure I don't run into end of project issues
August 18,2009 | 2 | Framework | 12 | 0 | 132.5 | Refactored some work to fall in line with best practices as discovered through reading
2009-08-20 | 2 | Test FrameworkManager | 12 | 10 | 130.5 | Login and logout, implementing VideoMediator, QuestionMediator and SectionTextMediator
2009-08-21 | 1 | Flash Video Player | 16 | 15 | 129.5 | Set up Controls for video player and defined more of the project data model ( mostly in xml )
2009-08-22 | 5 | Flash Video Player | 16 | 10 | 124.5 | Downloading placement videos, inserting xml, uml modelling, videoplayer engine, video player controls,
2009-08-22 | 5 | Navigation | 8 | 3 | 119.5 | navigation
2009-08-23 | 3 | Navigation | 8 | 0 | 116.5 | stop a user from going forward | TAGGED HERE
2009-08-23 | 5 | Video Player | 16 | 5 | 111.5 | more chaos in making videos work
2009-08-23 | 2 | Test FrameworkManager | 12 | 8 | 109.5 | Managing various system dependencies.. Like setting current section, logging out and in... Etc
2009-08-25 | 2 | Graphics Changes | 10 | -0.5 | 107.5 | Change requests asked for by Andre
6 1/2 Month Hiatus
2010-04-04 | 4 | Graphics Prep | 10 | -4.5 | 103.5 | Recieved final PSD was a ridiculous size. There was a ton of repetition and unecessary cruft. I removed this so the PSD would be manageable on my system while developing
2010-04-04 | 3 | Refactoring | 20 | 9 | 100.5 | Removed dependency on Login
2010-04-10 | 3 | Refactoring | 20 | 6 | 97.5 | Still rearranging various elements of old programming to accomidate different data approach, also reset the many aspects of the project files in general, like storage and versioning
2010-04-10 | 3 | Shared Object | 20 | 3 | 94.5 | Using the new tracking mechanism, so the user can leave an come back to where they left off.
2010-04-11 | 3 | Various | 10 | -7.5 | 91.5 | Added new graphic changes, new "Action" section, Home Page images, reset positioning, change in logo etc.
2010-04-11 | 4 | Flash Video Player | 16 | 1 | 87.5 | Some minor changes to the way the video works to account for flash specific bug, video converting, debugging etc
2010-04-11 | 4 | Test FrameworkManager | 12 | 4 | 83.5 | Refactored a lot of the framework so that it can handle a lot of different section layouts