## Sheet1
Date | #Hours | Task | Estimate | Sum | Running Total Left | Description | TAG
2009-08-09 | 4 | Graphics prep & PM | 10 | 6 | 157 | reorganizing photoshop file, speaking to Andre, planning approach
2009-08-12 | 3 | Graphics Prep & Email | 10 | 3 | 154 | Direct integration from photoshop to flash, attempted to convert vector paths from PS to AI... Didn't really work. Graphics should technically be vectors, but not enough time for me to change them. Emailed Andre about state of graphics
2009-08-13 | 1.5 | Graphics Prep | 10 | 1.5 | 152.5 | Integration of assets essentially complete. Expecting more assets and more changes.
2009-08-15 | 3 | Framework | 12 | 9 | 149.5 | Preparing the framework manager
2009-08-15 | 2 | Backend | 20 | 18 | 147.5 | backend data collection ( this is a stub object right now but will be converted to actual environment once this is known )
2009-08-16 | 5 | Framework | 12 | 4 | 142.5 | s
2009-08-16 | 6 | Backend | 20 | 12 | 136.5 | backend data collection ( will need to save remaining hours for database creation when I get it )
August 17,2009 | 2 | Framework | 12 | 2 | 134.5 | Framework research: Needed to do 2 hours of reading to ensure I don't run into end of project issues
August 18,2009 | 2 | Framework | 12 | 0 | 132.5 | Refactored some work to fall in line with best practices as discovered through reading
2009-08-20 | 2 | Test FrameworkManager | 12 | 10 | 130.5 | Login and logout, implementing VideoMediator, QuestionMediator and SectionTextMediator
2009-08-21 | 1 | Flash Video Player | 16 | 15 | 129.5 | Set up Controls for video player and defined more of the project data model ( mostly in xml )
2009-08-22 | 5 | Flash Video Player | 16 | 10 | 124.5 | Downloading placement videos, inserting xml, uml modelling, videoplayer engine, video player controls,
2009-08-22 | 5 | Navigation | 8 | 3 | 119.5 | navigation
2009-08-23 | 3 | Navigation | 8 | 0 | 116.5 | stop a user from going forward | TAGGED HERE
2009-08-23 | 5 | Flash Video Player | 16 | 5 | 111.5 | more chaos in making videos work
2009-08-23 | 2 | Test FrameworkManager | 12 | 8 | 109.5 | Managing various system dependencies.. Like setting current section, logging out and in... Etc
2009-08-25 | 2 | Graphics Changes | 10 | -0.5 | 107.5 | Change requests asked for by Andre
6 1/2 Month Hiatus
2010-04-04 | 4 | Graphics Prep | 10 | -4.5 | 103.5 | Recieved final PSD was a ridiculous size. There was a ton of repetition and unecessary cruft. I removed this so the PSD would be manageable on my system while developing
2010-04-04 | 3 | Refactoring | 20 | 9 | 100.5 | Removed dependency on Login
2010-04-10 | 3 | Refactoring | 20 | 6 | 97.5 | Still rearranging various elements of old programming to accomidate different data approach, also reset the many aspects of the project files in general, like storage and versioning
2010-04-10 | 3 | Shared Object | 20 | 3 | 94.5 | Using the new tracking mechanism, so the user can leave an come back to where they left off.
2010-04-11 | 3 | Graphics Prep | 10 | -7.5 | 91.5 | Added new graphic changes, new "Action" section, Home Page images, reset positioning, change in logo etc.
2010-04-11 | 4 | Flash Video Player | 16 | 1 | 87.5 | Some minor changes to the way the video works to account for flash specific bug, video converting, debugging etc
2010-04-11 | 4 | Test FrameworkManager | 12 | 4 | 83.5 | Refactored a lot of the framework so that it can handle a lot of different section layouts
April 18,2010 | 9 | XML Data Loader | 10 | 1 | 74.5 | Most work was actually in other areas but I'm pulling from this estimate to equalize hours. At this point the old estimate is nearly irrelevant as the project definition has changed drastically and the timeline has been completely blown out. Tasks completed were section continue navigation, video controls, and section text positioning / formatting.
April 22,2010 | 3 | Dynamic Image Loader | 5 | 2 | 71.5
2010-04-25 | 4 | Scroller | 0 | -4 | 67.5
2010-04-25 | 4 | Image Loader Framework | 5 | -2 | 63.5
2010-05-01 | 4 | Configuration | 16 | 12 | 59.5 | More or less worked on the image switching mechanism. Using Configuration pool, as that was also affected by these changes. i.e. Only certain sections are configured to swamp images
2010-05-03 | 4 | Configuration | 16 | 8 | 55.5 | Bullets, System for complex content
2010-05-30 | 8 | Various | 0 | -8 | 47.5 | a lot of struggling with the concept of the piece. Ripping out content text from psd, (there should be a file with content strings separated for easy farming) devising methods for specificity of each section. Original expected design has been greatly changed, and much of the design spec has come as a suprize. There is a lot of disorganization and a ton of missing content. Interactivity is not well thought out, but there is not enough hours left to deal with inconsistencies
2010-06-06 | 8 | Various | 0 | -16 | 39.5 | More of the same described above. From now on, I will no longer specifically itemize work. Everything is a mish mash, and I will simply move the content forward until there are no hours left
2010-06-07 | 2 | Various | 0 | -18 | 37.5
2010-06-19 | 10 | Various | 0 | -28 | 27.5
2010-06-20 | 8 | Various | 0 | -36 | 19.5
2010-06-21 | 1.5 | Various | 0 | -37.5 | 18
2010-06-22 | 1 | Verious | 0 | -38.5 | 17
June 23 2010 | 1 | Various | 0 | -39.5 | 16
June 24 2010 | 10 | Various | 0 | -49.5 | 6

## ref
TASK | Estimate | Used | Left Over
Flash Video Player | 16 | 15 | 1
Training Package Framework/Manager | 12 | 12 | 0
Test Framework/Manager | 12 | 12 | 0
Shared Objects | 2 | 2 | 0
Back End Data Collection | 20 | 19 | 1
Dynamic Image Loader | 5 | 5 | 0
Login/user registration | 10 | 0 | 10
Subtitle Implementation | 10 | 0 | 10
Text resizer | 16 | 0 | 16
Screen Reading Capabilities | 8 | 0 | 8
Navigation | 8 | 8 | 0
Configuration system | 16 | 8 | 8
Graphics implementation | 10 | 17.5 | -7.5
XML Loader/Data provider | 10 | 9 | 1
Extras | 0 | 41.5 | -41.5
Totals | 155 | 149 | 6